## Issues_New_17
Issues against installation & commissioning of 2HP Solar Water Pumps of Claro Energy Pvt. Ltd.
Sl. No. | District | Number of Solar Water Pumps Inspected (Nos) | Work Order No. | Work Order date | Name of the beneficiary | Actual date of Installation | Remarks/Issues | Data IN sheet
1 | Begusarai | 1 | 941 | 2019-05-31 | Md. Asraf Alam | 2019-06-22 | Beneficiary is not satisfied with the water discharge but the system is working as per specification. | Done
2 | Begusarai | 1 | 1834 | 2018-11-20 | Krishnanand Prasad | 2018-11-29 | Beneficiary is not satisfied with the water discharge but the system is working as per specification. | Done
3 | Gaya | 1 | 1361 | 2019-08-09 | Munna Khan | 2019-08-24 | Inspection not done yet by Firm. | Done
4 | Samastipur | 1 | 1441 | 2018-09-25 | ARUN CHANDRA CHOUDHERY | 2018-10-29 | Plant has been dismentaled by beneficiary due to Jammed Boring & ready for reinstallation after New One. | Done
5 | Samastipur | 1 | 1834 | 2018-11-20 | RAMA SHANKAR THAKUR | 2018-11-25 | Plant has been dismentaled by beneficiary due flood & ready for reinstallation after flood. | Done
6 | Samastipur | 1 | 44 | 2019-01-07 | SANJAY KUMAR DAS | 2019-01-01 | One Module (ECO 121812392) has been damaged due to storm on 09.03.2019 | Done
7 | Samastipur | 1 | 44 | 2019-01-07 | Upender Rai | 2019-01-21 | Plant has been dismentaled by beneficiary due to possibility of theft & ready for reinstallation after 2-3 months. | Done
8 | Samastipur | 1 | 430 | 2019-03-05 | YADUVANSH PRASAD RAY | 2019-02-21 | One Module (ECO 111825918) has been damaged due to storm on 09.03.2019 | Done
9 | Samastipur | 1 | 941 | 2019-05-31 | Vimla Tiwari | 2019-07-25 | Controller's keypad not working properly | Done
10 | Samastipur | 1 | 1834 | 2018-11-20 | Ram Udgar Rai | 2018-11-23 | Beneficiary is not satisfied with the water discharge but the system is working as per specification. | Done
11 | Samastipur | 1 | 2219 | 2018-12-28 | SANJIT KUMAR MISHRA | 2019-02-02 | Beneficiary is not satisfied with the water discharge but the system is working as per specification. | Done
12 | Sitamarhi | 1 | 239 | 2019-01-31 | Zigyasu | 2019-03-05 | Beneficiary has not signed on the Inspectionn Report. | Done
13 | Sitamarhi | 1 | 44 | 2019-01-07 | RAMVILAS THAKUR | 2019-01-18 | One module is found to be broken. | NA
14 | Sitamarhi | 1 | 1441 | 2018-09-25 | Nitesh Verma | 2018-10-30 | Installed at shadow area, discharge issue. | Done
15 | Sitamarhi | 1 | 285 | 2019-02-06 | Ganesh Rai |  | SWPS Installation is pending. | Done
16 | Sitamarhi | 1 | 144 | 2019-01-16 | Ajay Kumar | 2019-04-15 | Inspection not done yet by Firm. | Done
17 | West Champaran | 1 | 1441 | 2018-09-25 | Narendra Kumar Srivastava | 2018-10-18 | Plant has been dismentaled by beneficiary due to possibility of theft letter submitted by beneficiary. | NA
Total |  | 17

## Proper installation data
S.No | CID No | Site/Beneficiary Name | Father Name/Husband Name | Contact | Project Code | State | District | Block/Khand | Village | Capacity | VFD make | VFD serial number | Motor/Pump Make | Pump Serial No. | Installation date | Required data | Complaint date
1 | 100902 | Md Afroz alam | Karim Qureshi | 9931855153 | 19BR-BREDA-2HP-289 | Bihar | Begusarai | Ballia | Lakhmniya | 2 HP DC Submersible | Shakti | 2098744931 | Shakti | 2098666715 | 2019-06-26 | From date of installation to till date | NA
2 | 100740 | Krishna Nand Prasad | Mathuranand Prasad | 9709560940 | 19BR-BREDA-2HP-289 | Bihar | Begusarai | Sahebpur Kamal | Raghunathpur | 2 HP DC Submersible | Shakti | 2097594316 | Shakti | 2097594327 | 2018-11-29 | From date of installation to till date | 2018-12-07 | No fault found
3 | 100909 | Munna khan | Munna khan | 9572143600 | 19BR-BREDA-2HP-289 | Bihar | Gaya | Barachatti | Bazarkar | 2 HP DC Submersible | Shakti | 2107796511 | Shakti | 2107796511 | 2019-08-24 | From date of installation to till date | NA
4 | 100711 | Arun Chandra Chaudhary |  | 8084118182 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Shivjee Nagar | Shivjee Nagar | 2 HP DC Submersible | Shakti | 2097594336 | Shakti | 2097594339 | 2018-10-29 | From date of installation to till date | NA
5 | 100746 | Rama Shankar Thakur | Late Muneshwar Thakur | 9931245055 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Kalayanpur | Jagdish Paran | 2 HP DC Submersible | Shakti | 2097594308 | Shakti | 2097594329 | 2018-11-20 | From date of installation to till date | NA
6 | 100765 | Sanjay Kumar Das | Sri Ram Sobhit Das | 9304570173 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Samastipur | Rupnarayanpur Bela | 2 HP DC Submersible | Shakti | 2101368920 | Shakti | 2098666705 | 2019-01-01 | 1st jan 2019 to 3rd May 2019 and then 8th May 2019 to till date | 2019-05-08 | VFD parameter reset
7 | 100773 | Upendra Rai | Premlal Rai | 7277894357 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Patori | Dakshini Damaun | 2 HP DC Submersible | Shakti | 2098666701 | Shakti | 2098961519 | 2019-01-21 | From date of installation to till date | NA
8 | 100917 | Yaduvansh Prasad Rai | Rajo Rai | 9470271057 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Patori | Uttari Dhamoun | 2 HP DC Submersible | Shakti | 2098666703 | Shakti | 2098207537 | 2019-02-21 | From date of installation to till date | NA
9 | 100899 | Vimla tiwary | Vimla tiwary | 9308522455 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Samastipur | Rampur dudhpura | 2 HP DC Submersible | Shakti | 2105840519 | Shakti | 2105840519 | 2019-07-25 | 17/06/2019 to 15/04/2021 & then 08/07/2021 to till date | 2021-04-17 | VFD display replaced
10 | 100739 | Ram Udgar Rai | Gopal Rai | 8051213893 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Vidyapati Nagar | GarhSisai | 2 HP DC Submersible | Shakti | 2097594307 | Shakti | 2097594321 | 2018-11-23 | From date of installation to till date | NA
11 | 100758 | Sanjit Kumar Mishra | Late Suresh Mishra | 9430869766 | 19BR-BREDA-2HP-289 | Bihar | Samastipur | Bibhutpur | Chakhabib | 2 HP DC Submersible | Shakti | 2101368904 | Shakti | 2098666702 | 2019-02-02 | From date of installation to till date | NA
12 | 100784 | Zigyasu | Vijay Kumar Kumar | 9308888900 | 19BR-BREDA-2HP-289 | Bihar | Sitamarhi | Sursand | Bakhri | 2 HP DC Submersible | Shakti | 2101368907 | Shakti | 2101368907 | 2019-03-05 | From date of installation to till date | NA
13 | 100723 | Nitesh Verma | Shambu Prasad Verma |  | 19BR-BREDA-2HP-289 | Bihar | Sitamarhi | Runisaidpur | Belahi | 2 HP DC Submersible | Shakti | 2097594328 | Shakti | 2097594324 | 2018-10-30 | 30/10/2018 to 03/12/2018 & then 7/12/2018 to till date | 2018-12-04 | Wiring reset
14 | 100798 | Ganesh Rai | Ram Ashish Rai | 9973446768 | 19BR-BREDA-2HP-289 | Bihar | Sitamarhi | Sonebersha | Singhbahani | 2 HP DC Submersible | Shakti | 2098205710 | Shakti | 2098205723 |  | From date of installation to till date | NA
15 | 100775 | Ajay Kumar | Brahmdeo Rai | 9304442510 9955290518 | 19BR-BREDA-2HP-289 | Bihar | Sitamarhi | Sursand | Bathnaha | 2 HP DC Submersible | Shakti | 2098666713 | Shakti | 2098666709 | 2019-04-15 | From date of installation to till date | NA
16 | 100715 | Narendra Kishore Srivastava | Mangal Pd. Srivastava | 9931043888 | 19BR-BREDA-2HP-289 | Bihar | Bettiah (W.C) | Gaunaha | Bhibharwa | 2 HP DC Submersible | Shakti | 2097594347 | Shakti | 2097594333 | 2018-10-18 | From date of installation to till date | NA
17 | 100769 | Ramvilas Thakur | Asharphi Thakur | 9431064710 | 19BR-BREDA-2HP-289 | Bihar | Sitamarhi | Bajpatti | Madhopur Chaturi | 2 HP DC Submersible | Shakti | 2101368927 | Shakti | 2098207503 | 2019-01-18 | From date of installation to till date | NA